## Sheet1
ELECTION PLANNER
| 2004 |  | 2005 | [10 empty] | 2005 | 2006 | [10 empty] | 2006 | 2007 | [5 empty] | 2004 |  |  |  | OFFICER RESPONSIBLE | DATE COMPLETED | REMARKS
Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
TASK/MONTH | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT
1. POLLING PLACES
Assess OIC/PPLO Reports | bar: 2005 5 MAR
Inspection DRO/Staff | bar: 2006 15 JAN; 2007 27 JAN; 2004 33 JUL
Abolish/Appoint/Change Name | bar: 2006 15 JAN; 2007 27 JAN; 2004 33 JUL
Premises - Suitable/Alternative | bar: 2006 15 JAN; 2007 27 JAN; 2004 33 JUL
Mobiles (OIC Reports/Timetables) | bar: 2006 15 JAN; 2007 27 JAN; 2004 33 JUL
Prepoll Centres | bar: 2006 15 JAN; 2007 27 JAN; 2004 33 JUL
Seek Approvals | bar: 2007 27 JAN; 2004 33 JUL
Update Computer Systems/ERA Records | bar: 2005 9 JUL; 2006 15 JAN; 2006 21 JUL; 2007 27 JAN; 2004 33 JUL
Approved Polling Place Layout | bar: 2007 30 APR
Publicity Planning | bar: 2005 9 JUL; 2006 23 SEP; 2007 30 APR
2. STAFF - PERMANENT
Evaluate Performance/Roles | bar: 2005 9 JUL
Who Did What? | bar: 2005 9 JUL
Knowledge Levels/Skills | bar: 2005 9 JUL
Knowledge Needs/Skills | bar: 2005 9 JUL
Work Plans - Next Event | bar: 2006 21 JUL
Area Manager Oversight | bar: 2006 21 JUL; 2007 27 JAN; 2004 33 JUL
Staffing Contingency Plan | bar: 2006 15 JAN; 2006 21 JUL; 2007 27 JAN
3. STAFF - CASUAL
Evaluate Performance | bar: 2005 12 OCT
Assess - Stay/Replace/Move | bar: 2005 12 OCT
Identify Replacement Needs | bar: 2005 12 OCT
Assess Skills/Knowledge Required | bar: 2005 12 OCT
Prepare Task Sheets/Work Plans | bar: 2007 27 JAN
Update Computer Systems/ERA Records | bar: 2006 15 JAN; 2007 27 JAN
Confirm Eligibility | bar: 2006 15 JAN; 2007 27 JAN
Actively Recruit Replacement Staff | bar: 2007 27 JAN
4. STAFF - POLLING
Evaluate Performance - OIC/PPLO | bar: 2005 5 MAR
- Dec Officers | bar: 2005 9 JUL
- Polling Staff | bar: 2005 12 OCT
- Feedback | bar: 2005 12 OCT
Assessment - Stay/Replace/Move | bar: 2005 12 OCT
Update Staffing/Computer/ERA Records | bar: 2005 12 OCT; 2007 29 MAR
Confirm Availability to Work - Letter | bar: 2007 30 APR
Actively Recruit Replacement | bar: 2007 30 APR
5. TRAINING
Identify Deficiencies in Existing Divisional Program | bar: 2005 6 APR
Evaluation of Needs | bar: 2005 12 OCT
Set Training Goals | bar: 2005 12 OCT
Identify Needs - Permanent Staff | bar: 2005 12 OCT
- Casual Staff | bar: 2006 23 SEP
- Polling Staff | bar: 2007 31 MAY
Construct Training Pgrm - TOOS, ELMS, RMANS | bar: 2005 13 NOV; 2006 18 APR
Confirm Training Delivered & Understood | bar: 2007 27 JAN
Plan Training - TOPS, DEC, Prepoll | bar: 2007 30 APR to 2004 33 JUL
Rehearse Training Packages | bar: 2007 30 APR to 2004 33 JUL
Arrange TOPS Venues | bar: 2007 30 APR to 2004 33 JUL
6. POLLING MATERIALS & DISTRIBUTION
Office Cleanup | bar: 2005 5 MAR
Print/Amend Inventories - Actual Usage | bar: 2005 6 APR
Update Inventories/ERA Records | bar: 2005 6 APR; 2006 15 JAN; 2007 27 JAN; 2004 33 JUL
Identify Staffing Needs | bar: 2007 30 APR
Plan Material Receipt/Despatch | bar: 2007 30 APR
Delivery Schedules | bar: 2005 6 APR; 2006 15 JAN; 2007 27 JAN; 2004 33 JUL
Security Arrangements | bar: 2007 30 APR
Ballot Paper Storage/Accounting | bar: 2007 30 APR
Plan Prep/Package of Material | bar: 2007 30 APR
Plan Return of Material (Provincial & Country) | bar: 2007 30 APR
7. FINANCE
Comparison Forecast/Actual Last Event | bar: 2005 6 APR
Identify Changes Affecting Forecast | bar: 2005 9 JUL; 2006 15 JAN; 2006 21 JUL; 2007 27 JAN; 2004 33 JUL
Prepare Draft Forecast | bar: 2005 9 JUL
Review & Update Forecast with A/Manager | bar: 2006 15 JAN; 2006 21 JUL; 2007 27 JAN
Area Manager Approve/Advise on Forecast | bar: 2004 33 JUL
8. COMPUTER SYSTEMS
Evaluate Last Event Performance, Systems | bar: 2005 6 APR
Evaluate Office Affecting Forecast | bar: 2005 6 APR; 2005 9 JUL; 2004 33 JUL
Computer User Skills - Permanent | bar: 2006 15 JAN; 2007 27 JAN
- Casual | bar: 2007 30 APR to 2004 33 JUL
Work Plans/Checklist for Systems | bar: 2007 30 APR
Stores/Software | bar: 2005 6 APR; 2007 30 APR
Equipment Service/Maint/Replace | bar: 2007 27 JAN
Manual Backup Systems - ERA Record | bar: 2005 6 APR; 2005 12 OCT; 2006 18 APR; 2006 23 SEP; 2007 30 APR; 2004 33 JUL
9. ENROLMENT
RMANS Training | bar: 2006 24 OCT; 2007 30 APR