Table containing information put together by the IEC on timing, messages and techniques to create a specific plan stating what needed to be done when and by whom:

| When | What | Who |
| --- | --- | --- |
| By 19 April | Radio material on supp. registration | JC/SGJ |
| By 15 May | Radio material on objections | JC/SGJ |
| By 15 June | Radio material on transfers/deletions | JC/SGJ |
| By 31 July | Mark 1 Media kit | JC |
| By-elections | Press release | JC |
|  | GRTS announcement | GR |
|  | Traditional voter ed methods | SGJ |
| By June 2005 | Six more radio materials on key messages | JC/SGJ |

Contributors: Richard Carver